# Project Workplan

Project Title: Real Estate Valuation Prediction Using Multiple Regression
Duration: November 1 – December 6, 2025 (5 weeks)

| Week / Dates | Main Task | Subtasks / Details | Estimated Hours |
| --- | --- | --- | --- |
| Week 1 (Nov 1–7) | Model Specification & Setup | Load cleaned dataset and confirm variable types | 0.5 |
|  |  | Define and document regression formula | 0.5 |
|  |  | Fit baseline model using lm() and review coefficients | 1 |
|  |  | Interpret initial findings and note required adjustments | 0.5 |
|  | Subtotal |  | 2.5 hrs |
| Week 2 (Nov 8–14) | Model Refinement & Predictive Analysis | Test interaction terms; justify inclusion/exclusion | 1 |
|  |  | Try simple non-linear transformations (log/squared) | 1 |
|  |  | Refit model and compare results (R², Adj R²) | 0.5 |
|  |  | Generate individual predictor–response scatterplots | 1 |
|  | Subtotal |  | 3.5 hrs |
| Week 3 (Nov 15–21) | Diagnostics & Validation | Create and interpret diagnostic plots (Residuals, Q-Q, etc.) | 1.5 |
|  |  | Run and interpret VIF to check for collinearity | 1 |
|  |  | Validate model assumptions and summarize fixes (if any) | 0.5 |
|  | Subtotal |  | 3 hrs |
| Week 4 (Nov 22–28) | Result Visualization & Explanation | Generate boxplots for categorical variables (flat type, town) | 1 |
|  |  | Create final correlation heatmap and descriptive visuals | 1 |
|  |  | Write short interpretive summary of visuals | 0.5 |
|  | Subtotal |  | 2.5 hrs |
| Week 5 (Nov 29–Dec 6) | Summary & Reporting | Draft short project summary (findings, limitations, implications) | 1.5 |
|  |  | Compile all figures, tables, and R outputs into final Word doc | 1.5 |
|  |  | Proofread and finalize for submission | 1 |
|  | Subtotal |  | 4 hrs |
| TOTAL ESTIMATED TIME |  |  | ≈ 15–17 hours |